## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | DINESH KUMAR | 2024-02-10 | OCR not recognizing certain fonts | S2 | DINESH KUMAR | Logical | Improved OCR preprocessing | 2024-02-11 | Closed | Resolved with preprocessing
2 | DINESH KUMAR | 2024-02-15 | API authentication failure | S4 | DINESH KUMAR | Logical | Regenerated API keys | 2024-02-16 | Closed | Fixed authentication
3 | DINESH KUMAR | 2024-02-22 | Incorrect clustering output | S7 | DINESH KUMAR | Logical | Adjusted clustering parameters | 2024-02-23 | Closed | Parameters optimized
4 | DINESH KUMAR | 2024-03-05 | Web scraping blocked | S10 | DINESH KUMAR | User Interface | Used proxies and headers | 2024-03-06 | Closed | Bypassed restrictions

## Sheet2
Logical
User Interface
Maintainability
Standards
Others